## Slide 1: Northwind Q3 roadmap
Prepared for the product council
30 September 2026

## Slide 2: Where we are
Booking wait down from 9 days to 6
Call answer time missed target in August
Notes: Speaker note for slide 2: lead with the wait-time number.

## Slide 3: Member growth
Chart: 
| Q1 | Q2 | Q3
Members (thousands) | 118 | 124 | 131
Notes: Speaker note for slide 3: growth is mostly the Harbour clinic.

## Slide 4: What members asked for
Text reminders
Booking without a phone call
Shorter hold times
Notes: Speaker note for slide 4: keep this under a minute.

## Slide 5: Theme 1: faster booking
Online booking for all clinics by November
Same-day slots shown first
Notes: Speaker note for slide 5: keep this under a minute.

## Slide 6: Booking funnel
Chart: 
| Start | Pick slot | Confirm
Completed bookings (%) | 100 | 71 | 58
Notes: Speaker note for slide 6: keep this under a minute.

## Slide 7: Theme 2: reminders
Text reminders 48 hours and 2 hours before
Opt-out on every message
Notes: Speaker note for slide 7: keep this under a minute.

## Slide 8: Reminder pilot results
Chart: 
| Before | After
No-show rate (%) | 8.4 | 6.1
Notes: Speaker note for slide 8: keep this under a minute.

## Slide 9: Theme 3: call centre
Two extra Monday shifts
Call-back instead of hold
Notes: Speaker note for slide 9: keep this under a minute.

## Slide 10: Staffing plan
Hire 4 agents in October
Cross-train 6 clinic staff
Notes: Speaker note for slide 10: keep this under a minute.

## Slide 11: Risks
Vendor contract for SMS not signed
Riverside clinic still on the old scheduler

## Slide 12: Dependencies
Scheduler upgrade (IT)
SMS vendor security review (Security)
Notes: Speaker note for slide 12: keep this under a minute.

## Slide 13: Q4 milestones
October: SMS pilot at Riverside
November: online booking everywhere
December: call-back live
Notes: Speaker note for slide 13: keep this under a minute.

## Slide 14: Decisions needed
Approve SMS vendor spend of $42,000
Agree the Monday staffing change